7.1 Supply Proposal-Fane Ltd

Approach and Methodology

Project Plan

We envisage the project running as above but will adjust as required to deliver to LOCOG timelines

Key Project Milestones

December 2011- review of current staffing in the light of this and other on-going projects-identification of staffing requirements and advertising for local unemployed applicants via Jobcentre plus and DWP Work programme contractors.  Purchases of consumables and capital items in line with our Environmental Policy-including 100% recycled paper and Books from FSC approved supplier. Commence course development using existing knowledge and feedback from VGMs.

January 2012 Fane Ltd  staff training  to disseminate information from LOCOG briefing events-to ensure continuity of training and LOCG message. Training delivery commences

February 2012  Training fully underway,. Commencement of QA process with trainer observations and collection of course evaluation data- this will continue until project completion

March 2012-Resource review in the light of delivery so far- amendments made as required

April 2012- Staffing review –adjustments as required taking into consideration course take-up and predicted

May 2012- Resource updates/ Consumables purchase(if required)

June 2012 Training is completed (though we have planned for an additional 4 weeks (to cover unforeseen circumstances & ensure all required training is complete)

July 2012   Evaluation process completed by senior management

Aug 2012  Project debrief with trainers & final report to inform future bids and tenders. Redistribution of project resources as per ITT submission and donation of 1% of revenue made to Woodland Trust to further offset carbon emissions from project delivery

Management Structure

Overall Project Responsibility   Mike Green

Operational Management         Eileen Stemp ( LOCG contact for Operational Issues)

Project Administration               Lynne Philp   (LOCG contact for certification/finance)

Experience

Our  approach & methodology for the project from planning to evaluation

Pre-Course Preparation

Eileen Stemp our Operations Director will be available prior to commencement and throughout the project to deal with day to day operational issues and ensure that our trainers and courses comply with LOCOG & HSE requirements via our QA process.

We would be happy meet with VRMs/HR staff prior to courses (or converse via phone or email) or at any time during the project, to discuss delivery options & specific LOCOG requirements to allow us to tailor the course to their specific need in terms of.

- Specific Issues/Problems on Site or relating to Job role

- Start Times

- Delegate Experience/Job Role

- Individual Delegate Support Needs(additional resources or support required)

- Theory/Practical Mix

This would allow us to tailor the whole course delivery to the organisation and delegate requirements with the development/selection of appropriate content, trainers and support materials. Our trainers are all vastly experienced in their sector and subject area- and are accustomed to delivering to mixed groups of management and staff and mixed job roles. We do this on a regular basis for our Local Authority clients such as Newcastle City, Gateshead MB and Durham County Councils. If not known prior to the course, the background of each delegate is established at the outset and  during the course questions and perspectives are sought from all delegates-our support materials eg Case studies are written to work at any level and trainers can manage the learning process to ensure that each delegate gets the most out of their course.

We are also accustomed to delivering to groups with diverse abilities and support needs. We regularly train delegates with learning disabilities on our Working Links contract and have worked with delegates from Remploy, Neeta, Shaw Trust and Durham County Council who had diverse and complex support needs. On our Gateshead Council contract we regularly deliver training to groups of mixed ability for whom English is a second language.

The majority of our courses are entry level and therefore assume no prior knowledge on the part of the delegates-we always carry a range of resources- from case studies to pictures/photographs, so we have resources available at a range of levels and appropriate to different sectors. - we use visual resources such as video clips and photographs, a variety of printed and written material including quizzes and case studies- and each course has a significant practical element- utilising the most up to date equipment available for the course- we continually add to this, for example for our first aid courses where we use state of the art choking vests to add interest and value to the training.

Where support needs are identified prior to training we can organise additional support for a delegate during the course work or examination and make various adaptions to our materials- such as large print- or different coloured paper to assist a delegate with dyslexia

Delivery & Trainers

We aim to make each course, not only relevant to each individual but also entertaining, participative and funn.  All of our trainers have ‘real life’ first aid experience which is used to bring each course alive

Quotes from recent course delegates

‘Trainer was excellent and made the whole learning process easy and fun’                     ‘Trainer was brilliant, put me at ease, I was comfortable &relaxed and thoroughly enjoyed the course’

‘ Very entertaining & down to earth which made it easier to learn’                                     ‘The pace was super, the time flew by, best course I have attended in a long time!

(For trainer biography/cv please see Appendix 2)

The trainers assigned to deliver each course will be

- employed by Fane Ltd (not subcontracted)

- suitably qualified and experienced to deliver the training

- approved by the HSE.

- briefed on LOCOG requirements (as identified) and any problems or issues that need to be addressed during the course and any paperwork that needs to be completed

- Where possible trainers with relevant sector experience will be utilised eg Leisure, Hospitality, construction etc.

- observed and assessed in line with Fane Ltd internal moderation policy and will undertake regular CPD as required to ensure currency of knowledge and practice and quality of delivery. ( current trainer profiles are attached as appendix 2).

Delivery

All courses can be delivered flexibly to meet organisational need.

- 7 days a week

- Flexible start and finish times to suit

- early morning and evening sessions.

- All courses will include sector specific hand-outs and materials

- All courses can be tailored to meet delegates with additional support needs

- All delegates will receive a good quality professionally produced (course specific) text book

Approvals/Accreditation

Fane Ltd have been an HSE Approved training Centre for First Aid since 1996- we are approved to deliver Emergency First Aid at Work, First Aid at Work and  FAW Requalification training. As an HSE Approved Training Centre Fane Ltd confirm that we can deliver the training as per the specification, resulting in Nationally recognised Certificates for First Aid at work and Emergency First Aid at Work, (AED certificates would be certificates of attendance)

We also deliver 12GLH Paediatric First Aid course (endorsed by National Awarding Bodies EDI & OCN) – so should any of the delegates require some paediatric content to support them in their job roles that could easily be arranged

Our trainers have many years of experience in sectors such as Health,Care and Leisure ( please see trainer profiles), unusually for a training organisation, the majority being qualified nurses or emergency medical technicians with current NHS registration meaning we can deliver much more than a basic first aid course, being able to work expand on the syllabus to ensure that delegates questions are answered and organisational issues are resolved.

We have delivered first aid training across all sectors from 2hr taster sessions for home carers and volunteers to a bespoke HSE approved course for International Bodyguards, High Ropes and Adventure Personnel, Theme Park staff and other sporting pursuits. We also deliver for such diverse organisations as Mental Health Matters, ESPA, Tata(Steel), Swallow Hotels, Hodgson and Allon (Construction), Nampak (Europe), Accept Care and Industrial Landscapes each involving specific adjustments to our course to ensure it meets the needs of their sector.

Registration Details

HSE Registration 1738/96 (First Aid)

CIEH  Centre Number  52980( Health and Safety/Risk Assessment)

OCN Centre Number 56374(Paediatric First Aid)

EDI Centre Number  HCST2 (Paediatric First Aid)

HABC Centre number 10110 (Health and Safety/Risk Assessment)

AIFAWTO  Membership Number 574/10 (Association of Independent First Aid at Work Training Organisations)

Feedback and Evaluation

We strive to ensure that every course meets the delegates needs-and are constantly evaluating feedback and making adjustments and improvements to our provision

Internally we evaluate our training by collecting feedback from

- delegates

- employers

- our trainers

This feedback covers the learning experience, the support materials, the venue and the training delivery.

We will carry out regular trainer observations- looking at

- effectiveness of delivery,

- content

- compliance with legislation

- awarding body requirements.

This information is fed into our monthly board meetings- (where training quality is a standard agenda item) and evaluated and improvements implemented- being a small company with a flat management structure this can be turned around very quickly

Externally we are audited by The Chartered Institute of Environmental Health, the Health and Safety Executive, national awarding bodies EDI & OCN-and Working Links (for whom we have delivered training regionally and nationally)

In these external audits we are judged on our compliance with contractual and record keeping requirements, externally sourced feedback from course delegates and employers- and often observations of our training delivery- with some of our commercial contracts we also have other success parameters such as success rates on Nationally recognised qualifications and often job entry figures(on employment programmes and again any action points are dealt with at board meetings as a standard agenda item

We have recently successfully completed an HSE external audit with  the Health & Safety Executive giving our first aid provision an ‘excellent’ rating

We would be happy to participate in any LOCOG evaluation procedure on completion of the project-or release our own internal evaluation which we complete at the end of each project

Details of current services offered to any major/national organisations

Newcastle City Council Delivery of first aid food safety and health and safety training within one of the largest local authorities in the country- Fane Ltd are the preferred supplier for both Core Staff from all departments and also Early Years Foundation Stage Staff employed directly by the Authority and those who are self -employed Child Minders within Local Authority control

Working Links  Fane Ltd have been a preferred supplier for this national Welfare to Work Provider since 2005, delivering a range of pre-employment training to a wide range of clients often with complex barriers to learning. We work pan-sector covering, for example Health and Social Care, Retail/Warehousing, Customer Service, Catering/ Hospitality. In each sector we work with local employers to devise a course that meets the employers needs and legal requirements. We then support jobseekers through the course to enable them to achieve qualifications and experience that will allow them to fill vacancies advertised by the employer. We have delivered similar training for A4e, BTCV and JHP Training and we are a current specialist provider for Avanta on the DWP Work Programme

Sure Start   We have worked with Sure Start in our area for 5 yrs +. On this contract we support both their staff and customers in achieving nationally recognised qualifications in First Aid, Health and Safety and Food Safety and contribute to projects such as abc2 (an intervention for young parents aged under 19yrs)

Durham County Council Fane Ltd were the preferred supplier on a 5yr contract (ended May 2011) with the Authority to deliver compliance training to core staff across all Directorates

Southern Cross Plc  We delivered a programme of First Aid and Infection Control training across all Southern Cross homes in the North East-ensuring that each home had sufficient first aid cover to ensure the safety of residents and staff. The contract ran for 2 yrs ending in June 2011

Northumberland NHS Care Trust  Fane Ltd are an existing framework provider for the Trust and we are currently undergoing a tender process to provide first aid/health and safety and food safety training to all Trust staff.

Commercial Submission

We have based our calculations on the projected numbers in the ITT- and the availability of at least 1 training room per day- we would use a team of 6 trainers working flexible hours (in line with our Equality &Diversity principles) to ensure we had 7 days per week coverage and a variety of sector expertise available- we have therefore quoted below the monthly cost of one Full time equivalent(FTE) trainer over 7 days

Total cost for a duration of six months - £115,000

(of which we would donate 1% to the Woodlands Trust to help offset our carbon emissions)

Cost breakdown of benchmark price:

Number of trainers: 6

Cost per ‘full time equivalent’ trainer per month: £5400

Equipment & Consumables: £7700 (all remaining goods to be donated to charity at project end)

Certificates & ID Cards: £11,200

Text Books: £5040 (all remaining books to be donated to charity at project end)

Rate Card –We would offer a day rate for a group of 12 delegates for each course (per delegate costs also included for information) – The costs include, training, hand-outs, support materials and resources, all examination (and external examiner fees for FAW) and a good quality (course specific) text book for each of the 3 courses-we would also be happy to provide a day delegate rate on confirmation of numbers

| Course | Inclusive cost for 12 delegates | Equivalent per delegate cost for a full course |
| --- | --- | --- |
| HSE Approved Emergency First Aid at Work(EFAW) | £700 | £58 |
| HSE Approved First Aid at Work(FAW) | £1900 | £158 |
| Automated External Defibrillator (AED) | £350 | £29 |

Preferred Times for presentation (if selected) 5th December 9.00am or 10.30am

Appendix 1- Course Outlines

| HSE Approved Emergency First Aid at Work-6hrs |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Learning Outcomes: Candidates will be able to - demonstrate a clear understanding of their role as a first aider. - know how to summon help and be able to assess casualties using both the primary and secondary survey methods. - understand the importance of recording accidents in the work place. - identify different types of wounds and bleeds and understand the key principles of preventing cross contamination when treating wounds. - discuss treatment for wounds - identify the signs and symptoms of a casualty in shock and carry out effective treatment - identify the signs and symptoms of asphyxia and carry out effective treatment for a choking casualty - recognize an unconscious casualty and treat including treatment for a seizure - demonstrate effective CPR skills - demonstrate a thorough top to toe survey and be able to turn the casualty into the recovery position |  |  |  |  |  |
| Time | Content |  | Method | Resources | Assessment |
| 09.30 | House keeping Ice breakers Identifying any issues that may prevent students from completing the course |  | Discussion | Flipchart | N/A |
| 09.45 | Dealing with an Emergency Key legislation The principles of first aid The role of the first aider and the First Aid kit |  | Discussion Group Work | Powerpoint Photographs Emergency Scenario hand-out |  |
| 10.30 | Blood loss, types of wounds and cross infection, dealing with burns Applying dressings |  | Discussion Practical work | Blood Loss handout Powerpoint Dressing | Observation |
| 11.00 | Coffee Break |  |  |  |  |
| 11.10 | CPR/ Body Check/ Recovery | Practical work | Resus dolls, wipes and face shields |  | Observation |
| 12.00 | Lunch |  |  |  |  |
| 12.20 | Dealing with Shock-signs symptoms and treatment |  | Discussion | Powerpoint |  |
| 12.45 | Dealing with unconscious casualty Causes of Unconsciousness Dealing with an epileptic seizure |  | Practical Individual questions | Flip chart Powerpoint |  |
| 13.15 | Dealing with a choking casualty |  | Discussion Practical | Choking vest Resus doll | Observation |
| 13.45 | Practical CPR practice and formal assessment |  |  | Resus Dolls | Observation Oral questions |
| 15.15 | Theory examination-Paper or oral assessment dependent on delegate needs |  | Individual work | Exam papers/pens | Written/Oral if required |
| 15.45 | Course Closure & Evaluation |  | Discussion/Individual | Evaluation Forms/ Text books |  |
| 16.00 | Course Ends |  |  |  |  |

| Automated External Defibrillator -3hrs |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Learning Outcomes: At the end of the course the delegates will be able to - demonstrate a clear understanding of their responsibilities with regard to the use of an AED. - know how to summon help and be able to assess casualties using a primary survey. - identify health and safety issues that should be considered when using an AED - demonstrate effective CPR - demonstrate how to prepare the AED - demonstrate how to attach pads to the casualty - act on a range of prompts issued by the AED - understand reporting requirements after use |  |  |  |  |  |
| Time | Content | Method |  | Resources | Assessment |
| 09.30 | Registration/House keeping Ice breakers Identifying any issues that may prevent students from completing the course | Discussion |  | Flipchart | N/A |
| 09.45 | Dealing with an Emergency Carrying out a primary survey Types of AED/Location | Discussion |  | Powerpoint |  |
| 10.00 | CPR Practical Skill Check | Practical work |  | Resus dolls | Observation |
| 10.30 | Coffee Break |  |  |  |  |
| 10.40 | AED safety considerations & reporting requirements | Discussion | Powerpoint |  |  |
| 10.50 | Using AED | Demonstration/Practical work | AED, Resus doll |  | Observation |
| 11.30 | Assessment –CPR and AED | Practical Work in Pairs | AEDs and resus dolls |  | Observation and oral questioning |
| 12.30 | Course Closure & Evaluation | Discussion/Individual | Evaluation Forms Text books |  |  |
| 12.35 | Course Ends |  |  |  |  |

| HSE Approved First Aid at Work-18hrs Day 1 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Learning Outcomes: Day 1 The candidate will be able to - understand the importance of recording accidents in the work place - know how to summon help and be able to assess casualties using both the primary and secondary survey methods - demonstrate a clear understanding of their role as a first aider - identify different types of wounds and bleeds and understand the key principles of preventing cross contamination when treating wounds. - discuss treatment for wounds - identify the signs and symptoms of a casualty in shock and carry out effective treatment - demonstrate effective CPR skills - demonstrate a thorough top to toe survey and be able to turn the casualty into the recovery position - state the causes of unconsciousness |  |  |  |  |
| Time | Content | Method | Resources | Assessment |
| 09.30 | House keeping Ice breakers Identifying any issues that may prevent students from completing the course | Discussion | Flipchart | N/A |
| 09.45 | Dealing with an Emergency Key legislation The principles of first aid The role of the first aider and the FA kit | Discussion Group Work | Powerpoint Photographs Emergency Scenario hand-out |  |
| 10.30 | Blood loss, circulatory system types of wounds and cross infection, | Discussion | Blood Loss handout Powerpoint |  |
| 11.00 | Coffee Break |  |  |  |
| 11.10 | Dealing with wounds, foreign objects, pressure points, Applying dressings | Demonstration Practical work | Dressings/Powerpoint/ Photographs | Observation |
| 12.00 | Lunch |  |  |  |
| 12.20 | Dealing with internal bleeds, Shock signs, symptoms treatment | Discussion | Powerpoint |  |
| 13.00 | Dealing with unconscious casualty Causes of Unconsciousness | Discussion Group work | Flip chart |  |
| 13.30 | Practical Primary survey, CPR, secondary survey, recovery position | Demonstration Discussion Practical | Resus doll/face shields/wipes | Observation/Oral questioning |
| 15.30 | Recap /day1 end assessment | Individual questions-oral if required | Question papers | Written/ Oral questions |
| 15.55 | Any Questions | Discussion/Individual | Text books |  |
| 16.00 | Day 1 Ends |  |  |  |

| HSE Approved First Aid at Work Day 2 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Learning outcomes: Day 2 The candidate will be able to - identify signs and symptoms of heart attack and angina and demonstrate how to treat effectively - recognize and treat head injuries and stroke using FAST - identify causes of asphyxia and know how to treat effectively with demonstration of abdominal thrust using choking vest - identify types of poisons and discuss appropriate treatment for corrosive and non corrosive poisons. - identify signs and symptoms of anaphylactic shock and discuss appropriate treatment - explain the treatment for hypoglycemia and hyperglycemia and demonstrate how to deal with a casualty having an epileptic seizure - assess and treat burns using LADA - demonstrate eye wash procedure and treatment for embedded objects in the eye. - demonstrate competence in performing CPR a top to toe survey and turning a casualty into the recovery position |  |  |  |  |
| Time | Content | Method | Resources | Assessment |
| 09.30 | House keeping /Recap of Day1 | Individual Work | Recap hand-out | Written/oral questions |
| 10.00 | Heart-Anatomy and Physiology Signs & symptoms & treatment of angina and heart attackDealing with an Emergency Key legislation The principles of first aid The role of the first aider and the FA kit | Discussion | Powerpoint |  |
| 10.30 | Head Injuries-Concussion and compression Recognising and treating a stroke | Discussion Group Work | handout Powerpoint |  |
| 11.00 | Coffee Break |  |  |  |
| 11.10 | Causes of Asphyxia Recognition of chest wounds, choking and asthma | Demonstration Practical work Discussion | Powerpoint Choking Vest Resus Doll/Dressing | Observation |
| 12.00 | Lunch |  |  |  |
| 12.20 | Dealing with poisons Recognising & treating anaphylaxis | Discussion/ group work | Powerpoint photographs, handout/Epi pen | Observation/oral questioning |
| 13.00 | Dealing with diabetes and epilepsy | Discussion/Group work | Flip chart handout |  |
| 13.45 | Assessing and treating a burn/eye injuries | Discussion/Group work | Photographs and handouts | Observation |
| 14.30 | Practical CPR/recovery practice | Practical/Individual questions | Resus Dolls | Observation Oral questions |
| 15.45 | Recap Day 2 end assessment | Individual work | Question papers/pens | Written/Oral if required |
| 15.55 | Any Questions | Discussion/Individual |  |  |
| 16.00 | Day 2 Ends |  |  |  |

| HSE Approved First Aid at Work Day 3 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Learning Outcomes: Day 3 The candidate will be able to - understand of the different types of fractures and the importance of minimizing further damage to a fracture site - recognise the difference between a strain a sprain and a dislocation & explain appropriate treatment for each. - know when to turn a casualty with a suspected spinal injury and how to do this with a log roll technique - understand the theoretical and practical requirements of the first aid examination |  |  |  |  |  |
| Time | Content | Method | Resources | Assessment |  |
| 09.30 | House keeping Recap of day 1 and 2 | Discussion Individual work | Flipchart Handouts |  | Questioning |
| 10.15 | Recognising & treating fractures | Demonstration/Discussion/Group Work | Powerpoint/Photographs Slings |  | Observation |
| 11.00 | Coffee Break |  |  |  |  |
| 11.10 | Recognition and treatment of strains, sprains and dislocations | Discussion | Powerpoint |  |  |
| 11.30 | Spinal Injuries-recognition and treatment | Group work/Practical |  |  | Observation |
| 12.00 | Lunch |  |  |  |  |
| 12.20 | Practical practice and Exam preparation | Individual activity | Resus dolls |  | Observation |
| 14.00 | Oral/written and practical examination | Individual | Exam/Papers/Examiner Resus dolls |  | Observation/Questions |
| 15.45 | Results and Evaluation | Discussion | Evaluation forms |  |  |
| 16.00 | Course Ends |  |  |  |  |

Appendix 2 Trainer Bio/CV

Staff Profiles for LOCG First Aid Tender

| NAME | QUALIFICATIONS | IFL CIEH | EXPERIENCE |
| --- | --- | --- | --- |
| Mike Green Project Manager | BA Business (HR Training and Development) HNC Total Quality Management Advanced Food Hygiene (Level 4) Advanced HACCP (Level 4) Biotechnology /Microbiology Technical Apprenticeship TDLB D32/ D33 British College of Occupational Therapist Endorsed Handling and Moving trainer Fellow of the Royal Society of Health Back Care Professional Member Associate Member of the Chartered Society of Physiotherapy Registered CIEH/HABC Tutor for Food Safety Level 1-4 | AC033483 023032 | 12 yrs Biotechnology and Microbiology research and teaching, (University/ NHS/Local Authority) Trainer/NVQ Assessor 6yrs(Chemical/Food/QA Sector) 10 yrs management/Quality Assurance/ training experience in Health Care, Manufacturing, Food, Hospitality, Chemical sectors |
| Eileen Stemp Quality Control/Training Day 2 Day control of the contract | BSc (Hons) Registered Nurse level 2, Cert Ed, HSE Approved First Aid Trainer Advanced Cert Health & Safety at Work(Level 4). Advanced Food Hygiene.(Level 4) British College of Occupational Therapist Endorsed /CIEH Handling and Moving trainer | AC047157 011669 | 6 years nursing experience. 10 years as a part time tutor in Health And Social Care. 15 years of delivering and assessing First Aid at Work (HSE approved). 10 years of training in First Aid for Babies and Children. Registered tutor with CIEH for Food Hygiene and Health & Safety at work. |
| Margaret Gow First Aid | R.G.N. , S.C.M, S.D.N, Cert Ed. HSE Approved First aid trainer and assessor. | Examiner Only | 25 years of nursing experience 20 years of teaching Health Studies including First aid At Work, (HSE approved) First Aid for Babies and Children, (ASET Award) . Registered CIEH tutor for Food Hygiene. |
| Murshid Hussein First Aid Health and Safety Handling and Moving | C&G Cert Ed. HSE Approved First aid at work Trainer/Assessor Advanced CIEH health and Safety cert and Advanced CIEH Food Hyg cert. BCOT Endorsed /CIEH Handling and moving trainer | AE003156 019942 | 10 years experience as a trainer in the leisure industry at the pool side and in the gym.4 years experience in a supervisory/duty management role. |
| Sylvia Todd First Aid | RGN C&G 7307 D32/D33 HSE Approved First Aid trainer and assessor | AC054076 | 20 years nursing and private health care experience |
| Rita Birkbeck First Aid | Emergency Medical Technician(EMT) HSE Approved First Aid Trainer and Assessor | AE003116 | 20yrs experience in the ambulance service |
| Laura Baker First Aid | Resus Practioner,First Aid/ Immediate Life support Instructor, Acute Illness Management |  | 7yrs Royal Navy Leading Medical Assistant, 2yrs Resus Assistant (NHS) |
| Andrew Lowthian First Aid | Pool Lifeguard Award, HSE Approved First Aid Trainer, Community Sports Leader award, Ski Leader Certificate Level 5 Therapeutic Counselling, Level 5 Cognitive Behavioural therapy | AE003121 | 6yrs- Ambulance Officer(non emergency) 2yrs Advanced Ambulance Defibrillator drug Trained Technician 2yrs Pool Lifeguard |